#

|  |  |
| --- | --- |
| **Tender No: MCK/NBO/10/2021** | **Addendum No: 1** |
| **Tender Name: GIRL-H Program Evaluation** | **Date Issued: 7th July 2021** |

This letter amends the copy of the Tender Package as detailed below. Tenderers are required to sign and return this Addendum with the tender submission as confirmation that the Addendum was considered.

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

**Details of Addendum:**

\*The following sections of the Tender Package have been amended:

* All sections referencing the submission deadline of 8th July 2021 have been replaced by 12th July, 1159PM East African Time
* The table within section 6 seen as “original table below” has been replaced with the “amended table.”
	+ “original table below”

|  |  |
| --- | --- |
| **Expected GIRL-H Evaluation Timeframe and Sequencing Program Milestones/Outputs** | **Estimated Deadline** |
| Invitation to tender sent out | 26th June 2021 |
| Deadline for receipt of tenders | 8th July 2021 |
| Evaluation of tenders and shortlisting complete | 12th July 2021 |
| Evaluation Firm Appointed | 14th July 2021 |
| **Inception Phase** |   |
| Onboarding/Inception meeting held | 15th July 2021 |
| Draft Inception Report & Data Collection Tools created |  25th July 2021 |
| Review of inception & data tools by Mercy Corps completed | 28th July 2021 |
| Final Inception and data collection tools submitted | 1st August 2021 |
| **Implementation Phase** |   |
| Baseline |   |
| Questionnaire Scripting Developed, Reviewed & Completed | 6th August 2021 |
| Training of enumerators completed by | 13th August 2021 |
| Selection of control sites (GIRL-H) | 27th June 2021 |
| Fieldwork and data collection (conducted by) | 31st August 2021 |
| Final data cleaning and analysis completed by | 8th September 2021 |
| **Topline report highlighting baseline values of various indicators** | **10th September 2021** |
| The first draft of the detailed report shared with Mercy Corps | 17th September 2021 |
| Review of detailed report and feedback by Mercy Corps | 24th September 2021 |
| Revision of detailed report and submission by the firm | 30th September 2021 |
| Report presentation to project team by evaluation firm | 2nd October 2021 |
| **Midline Assessment** | **June to August 2022** |
| **Endline Evaluation** | **June to August 2023** |

* “amended table”

|  |  |
| --- | --- |
| **Expected GIRL-H Evaluation Timeframe and Sequencing Program Milestones/Outputs** | **Estimated Deadline** |
| Invitation to tender sent out | 26th June 2021 |
| Deadline for receipt of tenders | 12th July 2021 |
| Evaluation of tenders and shortlisting complete | 16th July 2021 |
| Evaluation Firm Appointed | 19th July 2021 |
| **Inception Phase** |   |
| Onboarding/Inception meeting held | 20th July 2021 |
| Draft Inception Report & Data Collection Tools created | 30th July 2021 |
| Review of inception & data tools by Mercy Corps completed | 28th July 2021 |
| Final Inception and data collection tools submitted | 4th August 2021 |
| **Implementation Phase** |   |
| Baseline |   |
| Questionnaire Scripting Developed, Reviewed & Completed | 9th August 2021 |
| Training of enumerators completed by | 13th August 2021 |
| Selection of control sites (GIRL-H) | 27th June 2021 |
| Fieldwork and data collection (conducted by) | 31st August 2021 |
| Final data cleaning and analysis completed by | 8th September 2021 |
| **Topline report highlighting baseline values of various indicators** | **10th September 2021** |
| The first draft of the detailed report shared with Mercy Corps | 17th September 2021 |
| Review of detailed report and feedback by Mercy Corps | 24th September 2021 |
| Revision of detailed report and submission by the firm | 30th September 2021 |
| Report presentation to project team by evaluation firm | 2nd October 2021 |
| **Midline Assessment** | **June to August 2022** |
| **Endline Evaluation** | **June to August 2023** |

\*The following sections have been added to the Tender Package:

No New Section Has Been Added

**All other terms and conditions remain unchanged.**

\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*

We acknowledge receipt of the above referenced Addendum to the Tender Package, and the Tender Addendum shall be incorporated into our Tender submission.

|  |  |  |  |
| --- | --- | --- | --- |
| Name:  |  |  | Stamp:  |
| Signature: |  |  |
| Date: |  |  |